## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[10 empty] | Risk | 2 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Predictive Placement Status and Graduation Year Calculation |  | Project Id: | IP23-000346 | Project Manager: | Harshada Topale |  |  | Assumption | 0 | 0 | 0 | 0 | 0 | 0
[10 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2023-09-05 | Project Team Lead: | Vaishnavi Pratap |  |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  |  | 6 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
3 | Risk | Inaccurate or missing data in the input datasets | Could lead to incorrect graduation year and placement predictions | Implement data validation checks and cleaning procedures during preprocessing. | Project Team Lead | High |  | Closed | Issue
4 | Risk | The machine learning model may overfit the training data | Reduced model generalization and inaccurate predictions | Apply cross-validation techniques and hyperparameter tuning to prevent overfitting. | Project Team Lead | Moderate |  | Closed | Dependency
5 | Issue | Data inconsistencies or errors in the source dataset | Could result in incorrect calculations and predictions | Establish data validation processes and address data issues as they arise. | Project Team Lead | High |  | Closed
6 | Issue | The machine learning model may not meet performance expectations | Could lead to inaccurate predictions and slow processing times | Continuously monitor model performance and optimize code for efficiency. | Project Team Lead | Moderate |  | Closed | Open
7 | Dependency | The success of the graduation year calculation depends on the quality of input data | Poor data quality may lead to inaccurate graduation year calculations | Collaborate with data providers to ensure data quality and consistency. | Project Team Lead | High |  | Closed | Closed
8 | Dependency | The prediction of placement status relies on the performance of the machine learning model | If the model underperforms, placement predictions may be unreliable | Regularly update and fine-tune the model to ensure accurate predictions. | Project Team Lead | Moderate |  | Closed
9 | [8 empty] | Critical
10 | [8 empty] | High
11 | [8 empty] | Moderate
12 | [8 empty] | Low
13 | [8 empty] | Negligible
14
15
16
17
18
19
20
21
22
23
24